## Capston Schedule
Capstone Schedule
| TASK NAME | START DATE | END DATE | ESTIMATED HOURS | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | February 1st |  |  |  |  | February 8th |  |  |  |  | February 15th |  |  |  |  | February 22nd |  |  |  |  | March 1st |  |  |  |  | March 8th |  |  |  |  | March 15th |  |  |  |  | March 22nd |  |  |  |  | March 29th |  |  |  |  | April 5th |  |  |  |  | April 12th
[8 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Hardware
| Order parts (teensy, adapter, bluetooth) | 2019-01-29 | 2019-02-04 | 1 | 5 | Rohan | 100% | bar: February 1st M to February 8th F; March 8th T to March 8th F
| Breadboard prototype hardware | 2019-02-01 | 2019-02-12 | 3 | 8 | Chris | 100% | bar: February 1st F to February 15th T; March 8th T to March 8th F
| Write source code for Teensy | 2019-01-29 | 2019-02-22 | 10 | 19 | Chris | 100% | bar: February 1st M to February 22nd F; March 8th T to March 8th F
| Design PCB | 2019-02-08 | 2019-02-15 | 10 | 6 | Chris | 100% | bar: February 8th M to February 22nd F; March 8th T to March 8th F
| Send PCB for manufacture | 2019-02-15 | 2019-02-22 | 2 | 6 | Chris | 100% | bar: March 8th T to March 8th F
| Solder components | 2019-02-23 | 2019-03-11 | 2 | 11 | Chris | 100% | bar: February 22nd M to March 15th M
| Validate hardware | 2019-03-11 | 2019-03-25 | 1 | 11 | Chris | 100% | bar: March 8th T to March 8th F; March 15th T to March 29th M
Android Application
| Wireframe application | 2019-01-29 | 2019-02-04 | 10 | 5 | Akash/Nathan | 100% | bar: February 1st M to February 8th F; March 8th T to March 8th F
| Define code structure (classes) | 2019-02-01 | 2019-02-04 | 5 | 2 | Rohan | 100% | bar: February 1st F to February 8th F; March 8th T to March 8th F
| Define UI in Android Studio | 2019-02-04 | 2019-02-15 | 10 | 10 | Akash | 100% | bar: February 8th M to February 22nd F; March 8th T to March 8th F
| Write source code of the application | 2019-02-16 | 2019-02-22 | 5 | 5 | Akash/Rohan | 100% | bar: March 8th T to March 8th F
| Black box testing of app | 2019-02-23 | 2019-03-25 | 15 | 21 | Akash/Rohan | 100% | bar: February 22nd M to March 29th M
Web Application
| Wireframe application | 2019-01-29 | 2019-02-04 | 10 | 5 | Nathan/Akash | 100% | bar: February 1st M to February 8th F; March 8th T to March 8th F
| Define UI | 2019-02-04 | 2019-02-15 | 3 | 10 | Rohan/Akash | 100% | bar: February 8th M to February 22nd F; March 8th T to March 8th F
| Write up server source code | 2019-02-16 | 2019-02-22 | 10 | 5 | Nathan | 100% | bar: March 8th T to March 8th F
| Write up client source code | 2019-02-16 | 2019-02-22 | 10 | 5 | Nathan | 100% | bar: March 8th T to March 8th F
| Black box testing of web app | 2019-02-23 | 2019-03-25 | 15 | 21 | Nathan | 100% | bar: February 22nd M to March 29th M
Documentation
| Specifications Report | 2019-01-29 | 2019-02-04 | 15 | 5 | Rohan | 100% | bar: February 1st M to February 8th F; March 8th T to March 8th F
| Critical Review Presentation | 2019-02-01 | 2019-02-12 | 5 | 8 | Team | 100% | bar: February 1st F to February 15th T; March 8th T to March 8th F
| Progress Report | 2019-02-13 | 2019-03-04 | 20 | 14 | Rohan | 100% | bar: February 15th W to March 8th F
| I/O Demo | 2019-03-25 | 2019-04-05 | 6 | 10 | Team | 100% | bar: March 8th T to March 8th F; March 22nd M to April 5th F
| Final Report | 2019-03-05 | 2019-04-10 | 20 | 27 | Rohan | 100% | bar: March 8th T to April 12th W
| Application Notes | 2019-03-05 | 2019-04-10 | 5 | 27 | Rohan | 100% | bar: March 8th T to April 12th W
| Video + Final Presentation | 2019-03-05 | 2019-04-10 | 10 | 27 | Team | 100% | bar: March 8th T to April 12th W
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])